## Bug Report
Wine Store Web Application Project
Project Name | Thirsty Wine
Created By | Viraj Pathak
Created Date | 16/07/2025
Approved By | Shiva Kumar
Approved Date | 23/07/2025
Bug_ID | Bug Description | Test_Case | Steps to Reproduce | Who Raised | Assigned To | Priority | Severiority | Status | Comments
BUG_001 | The "Name" field accepts numeric values, and no error is shown when entered. | TC_RG_003 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Click on 'My Account' Dropmenu 3. Select 'SignUp' option 4.Enter the Name | Viraj Pathak | Shiva Kumar | High | Major | Open | Name field should not accept numbers. Validation needed.
BUG_002 | The system allows users to enter an invalid email address without showing an error. | TC_RG_004 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Click on 'My Account' Dropmenu 3. Select 'SignUp' option 4.Enter the Credentials | Viraj Pathak | Shiva Kumar | High | Major | Open | Invalid email format should trigger error message.
BUG_003 | The system allows users to register with an invalid password | TC_RG_005 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Click on 'My Account' Dropmenu 3. Select 'SignUp' option 4.Enter the Credentials | Viraj Pathak | Shiva Kumar | High | Major | Open | Password validation missing.
BUG_004 | The system allows registration with an already used email without showing any error. | TC_RG_007 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Click on 'My Account' Dropmenu 3. Select 'SignUp' option 4.Enter the Credentials | Viraj Pathak | Shiva Kumar | High | Major | Open | Duplicate email registration should be blocked with error message.
BUG_005 | The user doesn't receive a confirmation email after registration. | TC_RG_008 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/register 2. Click on 'My Account' Dropmenu 3. Select 'SignUp' option 4. Enter new Account Details into the Mandatory Fields Name, Email, Password, Role 5. Click on 'Register' button 6. Check the email address used for registering the account | Viraj Pathak | Shiva Kumar | Medium | Major | Open | Email confirmation is essential after registration for user verification.
BUG_006 | The system automatically uses the Gmail ID as the username instead of the entered name. | TC_RG_009 | User should be able to use email as a valid username if no duplicates exist. | Viraj Pathak | Shiva Kumar | Medium | Major | Open | System should allow custom usernames instead of default Gmail ID.
BUG_007 | User login failed but it doesnt show any error about no match for e-mail address and password | TC_LP_002 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3. Go to the signup page 4. Enter the credentials 5. Click the login button | Viraj Pathak | Shiva Kumar | High | Critical | Open | No error message displayed for incorrect credentials.
BUG_008 | User login failed but it doesnt show any error about no match for e-mail address and password | TC_LP_003 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3. Go to the signup page 4. Enter the credentials 5. Click the login button | Viraj Pathak | Shiva Kumar | High | Critical | Open | Consistency issue with error messages across login attempts.
BUG_009 | User login failed but it doesnt show any error about no match for e-mail address and password | TC_LP_004 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3. Go to the signup page 4. Enter the credentials 5. Click the login button | Viraj Pathak | Shiva Kumar | Medium | Major | Open | Consistency issue with error messages across login attempts.
BUG_010 | There is no "Forgot Password" link or option available on the login page. | TC_LP_006 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3. Go to the signup page 4. Select the forget password option | Viraj Pathak | Shiva Kumar | Medium | Major | Open | Forgot password option is missing.
BUG_011 | It doesn't any error about multiple login attempts | TC_LP_009 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3. Go to the signup page 4. Enter the credentials 5. Click the login button | Viraj Pathak | Shiva Kumar | High | Critical | Open | No limit or error for multiple failed login attempts, leading to potential security issues.
BUG_012 | There is no social media option to login, user login with their registered credentials | TC_LP_010 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3. Go to the signup page 4. Enter the credentials 5. Click the login button | Viraj Pathak | Shiva Kumar | Medium | Major | Open | Social media login integration missing.
BUG_013 | There is no "Forgot Password" link or option available on the login page. | TC_LP_011 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3. Go to the signup page 4. Select the forget password option | Viraj Pathak | Shiva Kumar | Medium | Major | Open | Duplicate issue from BUG_010.
BUG_014 | There is no opions is there to recover the passwrod | TC_LP_013 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3. Go to the signup page 4. Select the forget password option | Viraj Pathak | Shiva Kumar | Medium | Major | Open | Password recovery options are absent.
BUG_015 | Profile section isn't open | TC_HP_006 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page | Viraj Pathak | Shiva Kumar | High | Major | Open | Profile section fails to load, needs debugging.
BUG_016 | The "promotion page" section does not display any products and shows a blank page instead. | TC_HP_014 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the Promotions option | Viraj Pathak | Shiva Kumar | High | Major | Open | Promotions section is broken, no content visible.
BUG_017 | The "Set&Gifts" section does not display any products and shows a blank page instead. | TC_HP_015 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the Set&Gifts option | Viraj Pathak | Shiva Kumar | High | Major | Open | Missing content in Set&Gifts section.
BUG_018 | The "What would you like" section does not display any products and shows a blank page instead. | TC_HP_018 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page | Viraj Pathak | Shiva Kumar | High | Major | Open | "What would you like" section fails to load products.
BUG_019 | Blog & News page is not responding | TC_HP_022 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the Blog & News option | Viraj Pathak | Shiva Kumar | High | Major | Open | Blog & News section is down or not responsive.
BUG_020 | instagramis not responding | TC_HP_023 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the we are on instagram option | Viraj Pathak | Shiva Kumar | High | Major | Open | Instagram link or API not functioning.
BUG_021 | "There is no product that matches the search criteria" message is not displayed. | TC_SH_002 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the search bar | Viraj Pathak | Shiva Kumar | High | Major | Open | The system should display a message when no search results match.
BUG_022 | There is no response from the search functionality,It didnt give any message | TC_SH_003 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the search bar | Viraj Pathak | Shiva Kumar | High | Critical | Open | Search functionality is not providing any feedback or results.
BUG_023 | It displays the red wine instead of White wine | TC_SH_014 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the search bar | Viraj Pathak | Shiva Kumar | Medium | Major | Open | Incorrect product display; the wrong category is being shown.
BUG_024 | It displays the red wine instead Rose wine | TC_SH_015 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the search bar | Viraj Pathak | Shiva Kumar | Medium | Major | Open | Incorrect product category being shown (Red wine instead of Rose wine)
BUG_025 | It displays the red wine instead of wine sets | TC_SH_016 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the search bar | Viraj Pathak | Shiva Kumar | Medium | Major | Open | Misclassification of products in search results (wine sets vs red wine).
BUG_026 | Decreasing item quantity in the cart does not update the cart correctly. | TC_AC_005 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the Add to Cart option 5. Go to the cart | Viraj Pathak | Shiva Kumar | High | Major | Open | Cart is not updating item quantities correctly after user modification.
BUG_027 | Wishlist is not displays the product | TC_WL_002 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. select wishlist button | Viraj Pathak | Shiva Kumar | High | Major | Open | Products added to the wishlist are not being displayed.
BUG_028 | The product is not added to the wishlist | TC_WL_005 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. select wishlist button | Viraj Pathak | Shiva Kumar | High | Major | Open | The wishlist functionality is not working as expected.
BUG_029 | User is able to enter numbers in the "Name" field in the address form. | TS_CA_004 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart 7. Go to the checkout option | Viraj Pathak | Shiva Kumar | Medium | Major | Open | Name field in the address form should only accept alphabetic characters.
BUG_030 | Checkoutf accepts the invlalid mobile number | TS_CA_005 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart 7. Go to the checkout option | Viraj Pathak | Shiva Kumar | High | Critical | Open | Mobile number validation is not working correctly during checkout.
BUG_031 | Checkout accepts the invlalid email | TS_CA_006 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart 7. Go to the checkout option | Viraj Pathak | Shiva Kumar | High | Critical | Open | Email validation is not being enforced during checkout.
BUG_032 | It doent't show the saved address | TS_CA_008 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart 7. Go to the checkout option | Viraj Pathak | Shiva Kumar | Medium | Major | Open | Saved address is not being retrieved or displayed during checkout.
BUG_033 | It accepts the invalid addres and proceed to checkout the payment | TS_CA_010 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart 7. Go to the checkout option | Viraj Pathak | Shiva Kumar | High | Major | Open | Address validation should prevent proceeding with invalid address details.
BUG_034 | It accepts the invalid current addres and proceed to checkout the payment | TS_CA_011 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart 7. Go to the checkout option | Viraj Pathak | Shiva Kumar | High | Major | Open | Invalid address should block the checkout process.
BUG_035 | The "City" field accepts numeric values, which should only accept alphabetic characters. | TS_CA_012 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart 7. Go to the checkout option | Viraj Pathak | Shiva Kumar | Medium | Major | Open | City field should restrict input to alphabetic characters only.
BUG_036 | The "State" field accepts numeric values, which should only accept alphabetic characters. | TS_CA_013 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart 7. Go to the checkout option | Viraj Pathak | Shiva Kumar | Medium | Major | Open | State field should only accept alphabetic characters.
BUG_037 | The "District" field accepts numeric values, which should only accept alphabetic characters. | TS_CA_014 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart 7. Go to the checkout option | Viraj Pathak | Shiva Kumar | Medium | Major | Open | District field should restrict input to alphabetic characters.
BUG_038 | The "Pincode" field accepts invalid pincode | TS_CA_015 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart 7. Go to the checkout option | Viraj Pathak | Shiva Kumar | High | Critical | Open | Pincode field is not validating input correctly; it should accept only valid pincodes
BUG_039 | User didn't receive any email after completing the checkout process | TS_CA_021 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart 7. Go to the checkout option | Viraj Pathak | Shiva Kumar | High | Major | Open | Order confirmation email is not sent after checkout completion.
BUG_040 | My account option is not clickable | TC_AO_002 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. In Home Page Right side there is a option called My Account | Viraj Pathak | Shiva Kumar | High | Critical | Open | "My Account" option is unresponsive and cannot be clicked.
BUG_041 | My account option is not responding/open | TC_AO_003 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. In Home Page Right side there is a option called My Account | Viraj Pathak | Shiva Kumar | High | Critical | Open | "My Account" button is not opening as expected.
BUG_042 | There is no my orders option is there | TC_AO_004 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. In Home Page Right side there is a option called My Account 5. my Orders option is there in my account drop down list | Viraj Pathak | Shiva Kumar | High | Major | Open | The "My Orders" option is missing from the "My Account" dropdown.
BUG_043 | There is no order information option is there in my account section | TC_AO_005 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. In Home Page Right side there is a option called My Account 5. my Orders information is there in my account drop down list | Viraj Pathak | Shiva Kumar | High | Major | Open | The "Order Information" option is missing from the "My Account" dropdown.
BUG_044 | There is no product returns option is there | TC_AO_006 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. In Home Page Right side there is a option called My Account 5. my Product Returns is there in my account drop down list | Viraj Pathak | Shiva Kumar | High | Major | Open | The "Product Returns" option is missing from the "My Account" dropdown.
BUG_045 | There is no your transaction option is there | TC_AO_007 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. In Home Page Right side there is a option called My Account 5. my Your Transactions is there in my account drop down list | Viraj Pathak | Shiva Kumar | High | Major | Open | The "Your Transactions" option is missing from the "My Account" dropdown.
BUG_046 | There is no order history option is there | TC_AO_008 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. In Home Page Right side there is a option called My Account 5. my Order history is there in my account drop down list | Viraj Pathak | Shiva Kumar | High | Major | Open | The "Order History" option is missing from the "My Account" dropdown.
BUG_047 | Category option shows sprankling products instead of White wine products | TC_CP_003 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Click on the one option in header section 3. Select White wine product option in category | Viraj Pathak | Shiva Kumar | Medium | Major | Open | The category section is displaying sparkling wine products instead of the selected category (White wine).
BUG_048 | Category Option shows sprankling products instead of Rose wine products | TC_CP_005 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Click on the one option in header section 3. Select Rose wine wine product option in category | Viraj Pathak | Shiva Kumar | Medium | Major | Open | The category section is displaying sparkling wine products instead of the selected category (Rose wine).
BUG_049 | Red wine product does not open when clicked. | TC_CA_002 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page | Viraj Pathak | Shiva Kumar | High | Critical | Open | The Red wine product link is broken or not opening when clicked.
BUG_050 | Rose wine product does not open when clicked. | TC_CA_003 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page | Viraj Pathak | Shiva Kumar | High | Critical | Open | The Rose wine product link is broken or not opening when clicked.
BUG_051 | White wine product does not open when clicked. | TC_CA_004 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page | Viraj Pathak | Shiva Kumar | High | Critical | Open | The White wine product link is broken or not opening when clicked.
BUG_052 | Sparkling wine product does not open when clicked. | TC_CA_005 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page | Viraj Pathak | Shiva Kumar | High | Critical | Open | The Sparkling wine product link is broken or not opening when clicked.
BUG_053 | Promotion page does not open when clicked. | TC_CA_006 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page | Viraj Pathak | Shiva Kumar | Low | Minor | Open | The Promotions page does not open when clicked.
BUG_054 | Set & Gifts page does not open when clicked. | TC_CA_007 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page | Viraj Pathak | Shiva Kumar | Medium | Major | Open | The Set & Gifts page does not open when clicked.
BUG_055 | FAQ Page does not open when clicked. | TC_SU_002 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page | Viraj Pathak | Shiva Kumar | Low | Minor | Open | The FAQ page does not open when clicked.
BUG_056 | Terms Of Use Option does not open when clicked. | TC_SU_003 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page | Viraj Pathak | Shiva Kumar | Medium | Major | Open | The Terms of Use page does not open when clicked.
BUG_057 | Privacy Policy Option does not open when clicked. | TC_SU_004 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page | Viraj Pathak | Shiva Kumar | Low | Minor | Open | The Privacy Policy page does not open when clicked.
BUG_058 | Delivery and payment page does not open when clicked. | TC_SU_005 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page | Viraj Pathak | Shiva Kumar | Medium | Major | Open | The Delivery and Payment page does not open when clicked.
BUG_059 | Returns and Exchange Option does not open when clicked. | TC_SU_006 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page | Viraj Pathak | Shiva Kumar | Medium | Major | Open | The Returns and Exchange page does not open when clicked.
BUG_060 | About Us Option does not open when clicked. | TC_SU_007 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page | Viraj Pathak | Shiva Kumar | Low | Minor | Open | The About Us page does not open when clicked.
BUG_061 | Contact Us Option does not open when clicked. | TC_SU_008 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page | Viraj Pathak | Shiva Kumar | Medium | Major | Open | The Contact Us page does not open when clicked.
BUG_062 | Review Page does not open when clicked. | TC_SU_009 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page | Viraj Pathak | Shiva Kumar | Low | Minor | Open | The Review page does not open when clicked.